## Forward Traceability
Requirements | Tests | Executions | Defects
OP-3 - As a user I want to be able to "Add Employee" | OP-5 - Verify that user can add an employee when the mandatory fields are filled | OrangeHRM - PASS | None
OP-3 - As a user I want to be able to "Add Employee" | OP-4 - Verify that user cannot add an employee when no field was fill in | OrangeHRM - PASS | None
OP-3 - As a user I want to be able to "Add Employee" | OP-6 - Verify how many employees can be added | OrangeHRM - PASS | None
OP-3 - As a user I want to be able to "Add Employee" - 1 defect | OP-8 - Verify that user cannot add an employee when required fields "First Name" and "Last Name" are filled with special characters | OrangeHRM - FAIL | OP-37 - Backlog - User can add an employee when required fields "First Name" and "Last Name" are filled with special characters
OP-3 - As a user I want to be able to "Add Employee" | OP-12 - Verify that user can add a picture in "Add Employee" section | OrangeHRM - PASS | None
OP-3 - As a user I want to be able to "Add Employee" - 1 defect | OP-7 - Verify that user cannot add an employee when required fields "First Name" and "Last Name" are filled with numbers | OrangeHRM - FAIL | OP-36 - Backlog - User can add an employee when required fields "First Name" and "Last Name" are filled with numbers
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-9 - Check if all the expected fields are available in employee "Personal Details" section | OrangeHRM - FAIL | OP-38 - Backlog - The list with the personal details is not as it is expected
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-10 - Check the "First name" as required field by not filling any data in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-11 - Check the "Last name" as required field by not filling any data in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-13 - Check the functionality of "Save" button at "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-14 - Verify that "Driver's License Number" from "Personal Details" section accepts any type of letters and special characters | OrangeHRM - FAIL | OP-39 - Backlog - The user is allowed to introduce letters and special characters in the "Driver's License Number"
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-15 - Verify that "License Expiry Date" accepts the format yyyy-mm-dd in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-17 - Verify that "Marital status" dropdown contains all the expected values | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-18 - Verify if the user can select an option from the dropdown list for "Marital status" in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-19 - Verify if the user can select an option from the dropdown list for "Nationality" in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-20 - Verify that "Date of Birth" accepts the format yyyy-mm-dd in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-21 - Verify if "Date of Birth" can't be set to future date in "Personal details" section | OrangeHRM - FAIL | OP-41 - Backlog - The user can select a future date for "Date of Birth" in the employee's Personal Details
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-22 - Verify that only one value from "Gender" radio buttons can be selected in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-23 - Verify that "First Name" field does not accept over 30 characters in employee "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-25 - Check the functionality of "Smoker" field in "Personal details" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-26 - Verify that "Blood Type" dropdown contains all the expected values | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-27 - Verify if the user can select one option from the dropdown list for "Blood Type" in "Personal details - Custom fields" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-28 - Check the functionality of "Save" button at "Personal details - Custom Fields" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-29 - Check that user can add one attachment in "Personal Details - Add Attachment" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-31 - Check if multiple uploads are allowed in "Personal Details - Add attachment" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-33 - Check the functionality of "Edit" button in "Personal Details - Add attachment" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-34 - Check that "Comment" field allows maxim 200 characters from "Personal Details - Add attachment" section | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section | OP-43 - Check that the field "Other ID" from "Personal Details " section accepts numbers | OrangeHRM - PASS | None
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-44 - Check that the field "Other ID" from "Personal Details " section does not accept letters | OrangeHRM - FAIL | OP-45 - Backlog - The user can add letters in the field "Other ID"
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-24 - Check that user cannot insert numbers in "Military service" field | OrangeHRM - FAIL | OP-40 - Backlog - The user can introduce numbers in the field "Military Service"
OP-2 - As a user I want to be able to add personal details from "Add Employee" section - 1 defect | OP-30 - Check that user cannot add one attachment larger than 1 MB in "Personal Details - Add Attachment" section | OrangeHRM - FAIL | OP-42 - Backlog - The user can add one attachment larger than 1 MB in "Personal Details - Add Attachment" section